## Schedule
CMPE 295A
| 2019-08-23 | 2019-08-30 | 2019-09-06 | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-04 | 2019-10-11 | 2019-10-18 | 2019-10-25 | 2019-11-01 | 2019-11-08 | 2019-11-15 | 2019-11-22 | 2019-11-29 | 2019-12-06
Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Finalize the details of the low-level and high level architecture with the advisor | bar: 2019-08-23 to 2019-08-30
Working on abstract and project proposal presentation | bar: 2019-08-30 to 2019-09-06
Environment setup and research about different sensors required for low level architecture interfacing | bar: 2019-09-06 to 2019-09-20
Aquire the sensors and hardware decided and run the sample code | bar: 2019-09-20 to 2019-09-27
Working on workbook 1 sections and giving the presentation | bar: 2019-09-27 to 2019-10-04
Collaborate the code and make the code work after collaborating effectively without any issues | bar: 2019-10-04 to 2019-10-18
Working on the individual sensor platforms and evaluating the performance based on system parameters | bar: 2019-10-11 to 2019-11-01
Working on workbook 2 sections and giving the presentation | bar: 2019-11-01 to 2019-11-08
Detailed evaluation of the platforms required for high level architecture | bar: 2019-11-08 to 2019-11-29
Generate an IEEE format project report with 2 chapters, complete the presentation and showcasing individual work done in semester | bar: 2019-11-29 to 2019-12-06
Offshore | 2019-08-23: Efforts in Person weeks | Total | Hours | Rate | Cost
PM | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  |  | 0.1 |  |  | 1 | 45 | 27.98 | 1259.1
PL | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  |  | 1 |  |  | 4.4 | 198 | 27.98 | 5540.04
Hardware 2 (TM) | 1 | 2 | 2 | 2 | 2 | 1.5 | 2 | 1.5 | 1.5 |  |  |  |  | 2 |  |  | 17.5 | 787.5 | 27.98 | 22034.25
Mechanical 2 (TM) | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 0.5 | 1 |  |  |  |  | 1 |  |  | 11.5 | 517.5 | 25 | 12937.5
SQA | 0.2 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.2 | 0.05 |  |  |  |  | 0.05 |  |  | 0.8 | 36 | 0 | 0
Total in USD | [19 empty] | 41770.89