## Schedule
TASKS FOR SAUMIL AND JAY | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03 | 2020-04-10 | 2020-04-17 | 2020-04-24 | 2020-05-01 | 2020-05-08 | 2020-05-15
Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
Interface sensors accelerometer, gyroscope, GPS. | bar: 2020-01-24 to 2020-02-07
Interface sensors Ultra-wideband beacon, LTE module, IMU sensors. | bar: 2020-01-31 to 2020-02-14
As per the project requirement create PCBs and hardware enclosures for the low-level hardware architecture. | bar: 2020-02-07 to 2020-02-21
Port ROS on Nvidia Jetson TX2 high- level platform and accompanying packages required for the creation of a Robotic System. | bar: 2020-02-28 to 2020-03-06
Understand ROS and explore the API’s from ROS on Jetson – All team members | bar: 2020-03-13 to 2020-03-20
Interface Camera and Lidar to Nvidia Jetson TX2 and receive data from them in a successful manner | bar: 2020-03-27 to 2020-04-17
Work on LIDAR for obstacle detection and develop a mechanism to create a signal | bar: 2020-03-27 to 2020-04-24
Deploy the low-level system and high- level system in a Robotic platform, Drone or autonomous vehicle to test and evaluate the performance of the system. | bar: 2020-05-01 to 2020-05-15
TASKS FOR VATSAL AND PRASHANT | 2020-01-24 | 2020-01-31 | 2020-02-07 | 2020-02-14 | 2020-02-21 | 2020-02-28 | 2020-03-06 | 2020-03-13 | 2020-03-20 | 2020-03-27 | 2020-04-03 | 2020-04-10 | 2020-04-17 | 2020-04-24 | 2020-05-01 | 2020-05-08 | 2020-05-15
Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
Interface sensors such as accelerometer, gyroscope, GPS | bar: 2020-01-24 to 2020-02-07
Work on PCB, finalize it and collaborate for integration of sensors | bar: 2020-02-14 to 2020-02-21
Connect the low-level hardware system to the cloud enabling the Internet of Things by using services such as AWS IoT or Google Cloud to monitor and analyze the sensor data. | bar: 2020-02-21 to 2020-03-13
Check the Camera on Jetson with the sample codes | bar: 2020-03-06 to 2020-03-13
Check the LIDAR on Jetson with the sample codes | bar: 2020-03-13 to 2020-03-20
Port ROS on Nvidia Jetson TX2 high- level platform and accompanying packages required for the creation of a Robotic System. | bar: 2020-03-06 to 2020-03-13
Interface Camera and Lidar to Nvidia Jetson TX2 and receive data from them in a successful manner. | bar: 2020-03-27 to 2020-04-17
Create 3D Maps for localization and deep learning applications for object detection, obstacle avoidance, and image segmentation. | bar: 2020-04-10 to 2020-04-24
Deploy the low-level system and high- level system in a Robotic platform, Drone or autonomous vehicle to test and evaluate the performance of the system. | bar: 2020-05-01 to 2020-05-15
Offshore | 2020-01-24: Efforts in Person weeks | Total | Hours | Rate | Cost
PM | 2020-01-24: 0.1; 2020-01-31: 0.1; 2020-02-07: 0.1; 2020-02-14: 0.1; 2020-02-21: 0.1; 2020-02-28: 0.1; 2020-03-06: 0.1; 2020-03-13: 0.1; 2020-03-20: 0.1; 2020-04-24: 0.1 | 1 | 45 | 27.98 | 1259.1
PL | 2020-01-24: 1; 2020-01-31: 0.5; 2020-02-07: 0.5; 2020-02-14: 0.5; 2020-02-21: 0.5; 2020-02-28: 0.1; 2020-03-06: 0.1; 2020-03-13: 0.1; 2020-03-20: 0.1; 2020-04-24: 1 | 4.4 | 198 | 27.98 | 5540.04
Hardware 2 (TM) | 2020-01-24: 1; 2020-01-31: 2; 2020-02-07: 2; 2020-02-14: 2; 2020-02-21: 2; 2020-02-28: 1.5; 2020-03-06: 2; 2020-03-13: 1.5; 2020-03-20: 1.5; 2020-04-24: 2 | 17.5 | 787.5 | 27.98 | 22034.25
Mechanical 2 (TM) | 2020-01-24: 1; 2020-01-31: 1.5; 2020-02-07: 1.5; 2020-02-14: 1.5; 2020-02-21: 1.5; 2020-02-28: 1; 2020-03-06: 1; 2020-03-13: 0.5; 2020-03-20: 1; 2020-04-24: 1 | 11.5 | 517.5 | 25 | 12937.5
SQA | 2020-01-24: 0.2; 2020-01-31: 0.05; 2020-02-07: 0.05; 2020-02-14: 0.05; 2020-02-21: 0.05; 2020-02-28: 0.05; 2020-03-06: 0.05; 2020-03-13: 0.2; 2020-03-20: 0.05; 2020-04-24: 0.05 | 0.8 | 36 | 0 | 0
Total in USD | [20 empty] | 41770.89